- HEALTH EQUITY

- Committee Focus

The Tampa Bay Healthcare Collaborative Health Equity Committee works to promote health equity and access to care, provide resources to share and offer capacity building opportunities.

- Committee Goals

- Promote health equity and increase community awareness

- Strengthen the skills, competencies and abilities of local organizations

- Provide support for members to engage in/implement activities to create health equity

- Contact Information

Committee Co-Chair: Tracy Christner, Executive Director, Empath Choices for Care, A Member of Empath Health, Email: tracychristner@empathhealth.org, Phone: (727) 536-7366

Committee Co-Chair: Lolita Dash-Pitts, Executive Director, Front Porch Community Development Association,	Email: dashfront@aol.com, Phone: (727) 804-2868

Staff Support:

- Lori James, Program Manager, Tampa Bay Healthcare Collaborative, Email: manager@tampabayhealth.org, Phone: (813) 655-4975

- Carrie Y. Hepburn, Executive Director, Tampa Bay Healthcare Collaborative, Email: director@tampabayhealth.org, Phone: (727) 812-4952

- HEALTH EQUITY

- WORKPLAN 2015

| GOAL I: Promote health equity and increase community awareness |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action Steps | Outcome | Timeline | Person(s) Responsible | Status |
| - Leverage health observances and cause days to promote health equity messages | Communication Plan Social Media Calendar Relevant content highlighting health equity and related information | Ongoing | Jocelyn (March), Tracy & Arwyn (April – health care decisions), Candice (Sept – infant mortality), Khaliah (cancer/health literacy) | In Progress |
| - Host a TBHC quarterly meeting | Quarterly Meeting Presentation – February 5, 2014 | February 2015 - Lost in Translation: Overcoming Cultural & Language Barriers | Carrie, Tracy, Lolita, Khaliah, Candice | Completed – 72 meeting attendees, representing 49 organizations |
| - Utilize DVD Loan Share Program to raise awareness among member organizations and conduct/facilitate community screenings - Unnatural Causes . . . is inequality making us sick? (4) - Race the power of an illusion (2) | ‘X’ # of participating members ‘X’ # of Community Screenings | Ongoing | Carrie, Khalilah | In Progress |

| GOAL II: Strengthen the skills, competencies and abilities of local organizations |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action Steps | Outcome | Timeline | Person(s) Responsible | Status |
| - Promote completion of cultural & linguistic competence assessment tool | Completed assessment results Action plan to address identified gaps | Ongoing | Committee | In Progress – |
| - Develop concept paper to establish a ‘cultural & linguistic competence cohort’ | Concept paper Funding support for CLC Cohort | April 2015 | Jocelyn, Allison, Candice, Lolita, Carrie | In Progress – workgroup is developing the concept paper to meet the Tau grant deadline (April 23rd) |
| - Submit grant proposals to support the CLCPA Cohort | Completed grant application(s) Funding support for CLC Cohort | April 2015 | All | Not Started |
| - Continue to partner with HERI (http://www.flheri.org/) | Implement the Health Disparities Research (HDR) Agenda for Florida | Ongoing | Carrie, Lolita | In Progress – Carrie & Lolita serve on the Community Leadership Board |

| GOAL III: Provide support for members to engage in/implement activities to create health equity |  |  |  |  |
| --- | --- | --- | --- | --- |
| Action Steps | Outcome | Timeline | Person(s) Responsible | Status |
| - Apply for funding opportunities as available to implement health equity activities | Grant funded program | Ongoing | All | In Progress – Submitted DentaQuest grant March 3rd |
| - Capture and disseminate key learnings and successes | Submit abstracts for national conferences | On Hold | All | Not Started |